## Schedule Maintenance CC ZPMC (hidden)
ANNUAL SCHEDULE MAINTENANCE MHC DAN CC TPKDB 2017
NO. | EQUIPMENT NAME | ACTION | SECTION | HM PER DES 2015 | MONTH/BULAN | [23 empty] | MONTH
[5 empty] | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
[5 empty] | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV
1 | MHC No.01 | Plan | Main Engine |  | JANUARY I: 18291; JANUARY III: 18541; FEBRUARY I: 18791; FEBRUARY III: 19041
|  | Realization |  |  | JANUARY III: 16/01/2017
|  | Plan | Hoist
Realization
|  | Plan | Slewing
Realization
|  | Plan | Boom
Realization
|  | Plan | Spreader
Realization
|  | Realization | Main Engine | 20124
|  |  | Auxiliary Engine | 22015.3
|  |  | Trolley | 5618.12
|  |  | Hoist | 8102.09
|  |  | Gantry | 455.29
|  |  | Boom | 156.35
|  |  | Spreader | 11150
2 | MHC No.02 | Plan | Main Engine |  | JANUARY I: 18935; JANUARY III: 19185; FEBRUARY I: 19435; FEBRUARY III: 19685; APRIL IV: 20685; JULY I: 21685; SEPTEMBER II: 22685; NOVEMBER III: 23685
|  | Realization |  |  | JANUARY III: 16/01/17; APRIL III: 500; MAY IV: 1000; JULY I: 1500; AUGUST II: 2000; SEPTEMBER III: 2500; OCTOBER IV: 3000; DECEMBER I: 3500
|  | Plan | Hoist |  | MAY III: 9100; JULY II: 8500; SEPTEMBER III: 8800; NOVEMBER III: 9100
|  | Realization |  |  | MARCH I: 11600; MAY I: 12000; JULY I: 11200; SEPTEMBER I: 11600; NOVEMBER I: 12000
|  | Plan | Slewing |  | MARCH I: 695; MAY I: 715; JULY I: 675; SEPTEMBER I: 695; NOVEMBER I: 715
|  | Realization |  |  | MARCH I: 250; MAY I: 260; JULY I: 240; SEPTEMBER I: 250; NOVEMBER I: 260
|  | Plan | Boom
Realization
|  | Plan | Spreader
|  | Realization |  |  | MARCH II: 18100; MAY II: 18600; JULY II: 17600; SEPTEMBER II: 18100; NOVEMBER II: 18600
|  | Realization | Main Engine | 21511
|  |  | Auxiliary Engine | 23282
|  |  | Trolley | 6647.13
|  |  | Hoist | 8775.33
|  |  | Gantry | 552.46
|  |  | Boom | 151
|  |  | Spreader | 14486
3 | CC No.02 | Plan | Main Engine |  | FEBRUARY I: 20465; MARCH II: 20965; APRIL III: 21465; MAY IV: 21965
|  | Realization |  |  | FEBRUARY II: 4018; MAY II: 4518; AUGUST II: 5018; NOVEMBER II: 5518
|  | Plan | Trolley |  | MARCH II: 6400; MAY II: 6700; JULY II: 7000; SEPTEMBER II: 7300; NOVEMBER II: 7600
|  | Realization |  |  | JANUARY III: 8550; MARCH III: 8950; MAY III: 9350; JULY III: 9850; SEPTEMBER III: 10350; NOVEMBER III: 10850
|  | Plan | Hoist |  | MARCH I: 569; MAY I: 589; JULY I: 609; SEPTEMBER I: 629; NOVEMBER I: 649
Realization
|  | Plan | Gantry
Realization
|  | Plan | Boom |  | JANUARY II: 200; MARCH II: 210; MAY II: 220; JULY II: 230; SEPTEMBER II: 240; NOVEMBER II: 250
Realization
|  | Plan | Spreader
|  | Realization |  |  | JANUARY III: 13600; MARCH III: 14100; MAY III: 14600; JULY III: 15100; SEPTEMBER III: 15600; NOVEMBER III: 16100
|  | Realization | Main Engine | 15356
|  |  | Auxiliary Engine | 510
|  |  | Trolley | 4312.46
|  |  | Hoist | 6020.49
|  |  | Gantry | 427.42
|  |  | Boom | 135.26
|  |  | Spreader | 10078
4 | CC No.03 | Plan | Main Engine |  | FEBRUARY I: 25017; MARCH II: 25517; APRIL III: 26017; MAY IV: 26517; JULY I: 27017; AUGUST II: 27517; SEPTEMBER III: 28017; OCTOBER IV: 28517; DECEMBER I: 29017
|  | Realization |  |  | FEBRUARY I: 4469; MAY I: 4969; AUGUST I: 5469; NOVEMBER I: 5969
|  | Plan | Trolley |  | MARCH II: 6500; MAY II: 6800; JULY II: 7100; SEPTEMBER II: 7400; NOVEMBER II: 7700
|  | Realization |  |  | MARCH II: 10550; MAY III: 10950; JULY III: 11350; SEPTEMBER III: 11750; NOVEMBER I: 712; NOVEMBER III: 12150
|  | Plan | Hoist |  | MARCH I: 632; MAY I: 652; JULY I: 672; SEPTEMBER I: 692; NOVEMBER I: 268
|  | Realization |  |  | JULY I: 248; SEPTEMBER I: 258
|  | Plan | Gantry
|  | Realization |  |  | MARCH I: 228; MAY I: 238
|  | Plan | Boom
Realization
|  | Plan | Spreader
|  | Realization |  |  | JANUARY II: 16000; MARCH II: 16500; MAY II: 17000; JULY II: 17500; SEPTEMBER II: 18000; NOVEMBER II: 18500
|  | Realization | Main Engine | 19824
|  |  | Auxiliary Engine | 683
|  |  | Trolley | 5318.27
|  |  | Hoist | 7678.52
|  |  | Gantry | 490.14
|  |  | Boom | 158.03
|  |  | Spreader | 12564
5 | CC No.05 | Plan | Main Engine |  | JANUARY IV: 20920; MARCH I: 21420; APRIL II: 21920; MAY III: 22420; JUNE IV: 22920; AUGUST I: 23420; SEPTEMBER II: 23920; OCTOBER III: 24420; NOVEMBER IV: 24920
|  | Realization |  |  | FEBRUARY IV: 3432; JUNE IV: 3932; SEPTEMBER IV: 4432; DECEMBER IV: 4932
|  | Plan | Trolley |  | MARCH I: 5130; MAY I: 5430; JULY I: 5730; SEPTEMBER I: 6030; NOVEMBER I: 6330
|  | Realization |  |  | JANUARY II: 10150; MARCH II: 10550; MAY II: 10950; JULY II: 11350; SEPTEMBER II: 11750; NOVEMBER II: 12150
|  | Plan | Hoist |  | JANUARY II: 555; MARCH II: 575; MAY II: 595; JULY II: 615; SEPTEMBER II: 635; NOVEMBER II: 655
|  | Realization |  |  | JANUARY III: 228; MARCH III: 238; MAY III: 248; JULY III: 258; SEPTEMBER III: 268; NOVEMBER III: 278
|  | Plan | Gantry
Realization
|  | Plan | Boom
Realization
|  | Plan | Spreader
Realization
|  | Realization | Main Engine | 15806
|  |  | Auxiliary Engine | 743
|  |  | Trolley | 3019.11
|  |  | Hoist | 5579.1
|  |  | Gantry | 434.34
|  |  | Boom | 165.56
|  |  | Spreader | 9418
6 | CC No.06 | Plan | Main Engine |  | JANUARY IV: 20920; MARCH I: 21420; APRIL II: 21920; MAY III: 22420; JUNE IV: 22920; AUGUST I: 23420; SEPTEMBER II: 23920; OCTOBER III: 24420; NOVEMBER IV: 24920
|  | Realization |  |  | FEBRUARY IV: 3432; JUNE IV: 3932; SEPTEMBER IV: 4432; DECEMBER IV: 4932
|  | Plan | Trolley |  | MARCH I: 5130; MAY I: 5430; JULY I: 5730; SEPTEMBER I: 6030; NOVEMBER I: 6330
|  | Realization |  |  | JANUARY II: 10150; MARCH II: 10550; MAY II: 10950; JULY II: 11350; SEPTEMBER II: 11750; NOVEMBER II: 12150
|  | Plan | Hoist |  | JANUARY II: 555; MARCH II: 575; MAY II: 595; JULY II: 615; SEPTEMBER II: 635; NOVEMBER II: 655
|  | Realization |  |  | JANUARY III: 228; MARCH III: 238; MAY III: 248; JULY III: 258; SEPTEMBER III: 268; NOVEMBER III: 278
|  | Plan | Gantry |  | FEBRUARY IV: 2000; APRIL IV: 2500; JUNE IV: 3000; AUGUST IV: 3500; OCTOBER IV: 4000; DECEMBER IV: 4500
Realization
|  | Plan | Boom
Realization
|  | Plan | Spreader
Realization
[12 empty] | MUHAMMAD SUAIB | [11 empty] | SYAHMAN SIREGAR | [7 empty] | MUHAMMAD SUAIB | [13 empty] | SYAHMAN SIREGAR
[11 empty] | ASST.MANAGER PERALATAN DAN INSTALASI TPKDB | [12 empty] | MAINTENANCE PT.ASHA PORTINDO | [5 empty] | ASST.MANAGER PERALATAN DAN INSTALASI TPKDB | [14 empty] | MAINTENANCE PT.ASHA PORTINDO

## SCHEDULE
ANNUAL SCHEDULE MAINTENANCE 12 UNIT ARTG | [64 empty] | #REF!
TERMINAL PETIKEMAS BELAWAN FASE 2
NO. | CRANE ID |  | MONTH | [59 empty] | REMARKS
|  | DESC. | JANUARY'22 |  |  |  |  | FEBRUARY'22 |  |  |  |  | MARCH'22 |  |  |  |  | APRIL'22 |  |  |  |  | MEI'22 |  |  |  |  | JUNE'22 |  |  |  |  | JULY'22 |  |  |  |  | AUGUST'22 |  |  |  |  | SEPTEMBER'22 |  |  |  |  | OKTOBER'22 |  |  |  |  | NOVEMBER'22 |  |  |  |  | DECEMBER'22
|  |  | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V
1 | ARTG 01 | PLAN DATE | JANUARY'22 I: 6; FEBRUARY'22 II: 6; MARCH'22 I: 4; APRIL'22 II: 6; MEI'22 II: 10; JUNE'22 II: 9; JULY'22 II: 6; AUGUST'22 I: 5; SEPTEMBER'22 II: 5; OKTOBER'22 I: 6; NOVEMBER'22 I: 4; DECEMBER'22 II: 5 | PM 250 |  | PM 500
|  | REAL DATE | [60 empty] | 1. Inspection cable ways & cable rack |  | 1. All Item PM 250
|  | HM REAL | [60 empty] | 2. Inspect Gear Reducer Oil Level, add if needed |  | 2. Brake Inspection (for Gantry, Hoist)
2 | ARTG 02 | PLAN DATE | JANUARY'22 IV: 24; FEBRUARY'22 IV: 24; MARCH'22 IV: 24; APRIL'22 V: 26; MEI'22 IV: 24; JUNE'22 IV: 24; JULY'22 V: 26; AUGUST'22 IV: 24; SEPTEMBER'22 V: 27; OKTOBER'22 IV: 26; NOVEMBER'22 IV: 24; DECEMBER'22 V: 26 | (for all motor) |  | 3. Noise and Vibration Inspection (Trolley)
|  | REAL DATE | [60 empty] | 3. Check all tightening bolt gear reducer |  | 4. Hoist limit switch function check
|  | HM REAL | [60 empty] | 3. Check MotorWiring Connection |  | 5. Noise and Vibration check
3 | ARTG 03 | PLAN DATE | JANUARY'22 II: 15; FEBRUARY'22 III: 15; MARCH'22 III: 15; APRIL'22 III: 12; MEI'22 III: 19; JUNE'22 III: 17; JULY'22 III: 12; AUGUST'22 III: 15; SEPTEMBER'22 III: 14; OKTOBER'22 II: 12; NOVEMBER'22 III: 14; DECEMBER'22 III: 15 | 4. Check Intercom Function |  | (Drum Hoist, Motor Hoist & ACM)
|  | REAL DATE | [60 empty] | 5. Check Audible and Beacon Function |  | 6. Sheaves Inspection
|  | HM REAL | [60 empty] | 6. Testing Boogie Turning Feature |  | 7. Operation Mechanism check of Cable basket
4 | CC.05 | ENGINE | [60 empty] | 7. Check All Limit Switch position |  | 8. Slip Ring Inspection
|  | HOIST | [60 empty] | 8. Check Trolley cubicle condt. |  | (contact, alignment, tightness, cleaning, connection)
|  | TROLLEY | [60 empty] | (fan, heating and lighting)
GANTRY
BOOM
SPREADER
4 | ARTG 04 | PLAN DATE | JANUARY'22 IV: 24; FEBRUARY'22 IV: 23; MARCH'22 IV: 23; APRIL'22 V: 27; MEI'22 IV: 23; JUNE'22 IV: 23; JULY'22 V: 27; AUGUST'22 IV: 23; SEPTEMBER'22 IV: 23; OKTOBER'22 IV: 27; NOVEMBER'22 IV: 23; DECEMBER'22 IV: 22
|  | REAL DATE | [60 empty] | 9. Check Anemometer Cond. & Funct. |  | (contact, alignment, tightness, cleaning, connection)
|  | HM REAL | [60 empty] | 10. Check all Wire rope visually |  | 9. Cable Reel Inspection
5 | ARTG 05 | PLAN DATE | JANUARY'22 III: 18; FEBRUARY'22 III: 18; MARCH'22 III: 18; APRIL'22 IV: 18; MEI'22 III: 18; JUNE'22 III: 16; JULY'22 IV: 18; AUGUST'22 III: 18; SEPTEMBER'22 IV: 19; OKTOBER'22 III: 18; NOVEMBER'22 III: 17; DECEMBER'22 III: 14 | (deform, broken, no corrosion, |  | (Cleaning passages, connection, sealing of gland cable)
|  | REAL DATE | [60 empty] | Clamps position, min. 5xd free wirerope |  | 10. Checking number of start of brakes
|  | HM REAL | [60 empty] | ,lubrication wirerope) |  | 11. Electrical Inspection
6 | ARTG 06 | PLAN DATE | JANUARY'22 I: 3; FEBRUARY'22 I: 3; MARCH'22 I: 2; APRIL'22 I: 1; MEI'22 II: 9; JUNE'22 I: 3; JULY'22 I: 1; AUGUST'22 I: 3; SEPTEMBER'22 I: 2; OKTOBER'22 I: 3; NOVEMBER'22 I: 1; DECEMBER'22 I: 1 | 12. Inspect all Power Connection & JB |  | (wiring connection, fuses, telephone, intercom,
|  | REAL DATE | [60 empty] | 13. Inspect Twistlock Mounting & Locking Pin |  | lighting, Battery & UPS)
|  | HM REAL | [60 empty] | 14. Inspect Cable Basket and its Mounting
7 | ARTG 07 | PLAN DATE | JANUARY'22 II: 13; FEBRUARY'22 III: 14; MARCH'22 II: 11; APRIL'22 III: 13; MEI'22 II: 11; JUNE'22 II: 8; JULY'22 III: 13; AUGUST'22 III: 14; SEPTEMBER'22 III: 15; OKTOBER'22 II: 13; NOVEMBER'22 II: 10; DECEMBER'22 II: 9 | 15. Inspect all Headblock Locking mechanism |  | PM 750
|  | REAL DATE | [60 empty] | 16. Function Test all spreader feature |  | 1. All Item PM 250
|  | HM REAL | [60 empty] | (telescopic, lock unlock, sensor, limit switch) |  | 2. Lubrication Access Gate
8 | ARTG 08 | PLAN DATE | JANUARY'22 IV: 25; FEBRUARY'22 IV: 25; MARCH'22 IV: 25; APRIL'22 V: 25; MEI'22 IV: 25; JUNE'22 IV: 21; JULY'22 V: 25; AUGUST'22 IV: 25; SEPTEMBER'22 V: 26; OKTOBER'22 IV: 25; NOVEMBER'22 IV: 22; DECEMBER'22 IV: 21 | 17. Check Spreader JB and Electrical Cubicle |  | 3. Greasing (NPX-NL2)
|  | REAL DATE | [60 empty] | (no leak, rubber seal, wire connection) |  | (wheel bearing, guide roller, Aux & Main Hoist Drum,
|  | HM REAL | [60 empty] | 18. Check Telescopic Rail, Beam & features |  | Hoist Drum Coupling, Wedges Head fitting
9 | ARTG 09 | PLAN DATE | JANUARY'22 II: 10; FEBRUARY'22 II: 10; MARCH'22 II: 10; APRIL'22 III: 11; JUNE'22 II: 10; JULY'22 III: 11; AUGUST'22 II: 10; SEPTEMBER'22 II: 8; OKTOBER'22 II: 11; NOVEMBER'22 II: 8; DECEMBER'22 II: 8 | 19. Inspect AGS (No Leak in Hose & Hub) |  | horizontal pin, Spreader Bearing, load cell)
|  | REAL DATE | [60 empty] | 20. Inspect Cable reel and cable guide |  | 4. Greasing Shell Wirerope
|  | HM REAL | [60 empty] | (no noise) |  | (wirerope aux & main, sliding plate spreader
10 | ARTG 10 | PLAN DATE | JANUARY'22 III: 19; FEBRUARY'22 III: 17; MARCH'22 III: 19; APRIL'22 IV: 19; MEI'22 III: 17; JUNE'22 III: 14; JULY'22 IV: 19; AUGUST'22 III: 19; SEPTEMBER'22 IV: 20; OKTOBER'22 III: 19; NOVEMBER'22 III: 16; DECEMBER'22 III: 13 | 21. Inspect for fan and heater |  | 5. Inspection Leakage for motor coupling
|  | REAL DATE | [60 empty] | 22. Inspect for leakage in E-Room |  | 6. Wirerope Inspection (diameter & tightening torque)
|  | HM REAL | [60 empty] | 23. Inspect the E-Stop and it's accs |  | 7. Between Sheaves and Wirerope Inspection
11 | ARTG 11 | PLAN DATE | JANUARY'22 II: 14; FEBRUARY'22 III: 16; MARCH'22 III: 14; APRIL'22 III: 14; MEI'22 II: 13; JUNE'22 III: 13; JULY'22 III: 14; AUGUST'22 III: 16; SEPTEMBER'22 III: 16; OKTOBER'22 II: 14; NOVEMBER'22 III: 15; DECEMBER'22 III: 12 | 24. Inspect for AC |  | (Air Gap Welds sheaves, bracket)
|  | REAL DATE | [60 empty] | 25. Inspect fire extinguisher and tes function for AFS |  | 8. Fire Suppresion Pipe Inspection
|  | HM REAL | [62 empty] | (Operation, control Valve and replace
12 | ARTG 12 | PLAN DATE | JANUARY'22 IV: 28; FEBRUARY'22 V: 28; MARCH'22 V: 29; APRIL'22 V: 28; MEI'22 V: 30; JUNE'22 V: 30; JULY'22 V: 28; AUGUST'22 IV: 26; SEPTEMBER'22 V: 28; OKTOBER'22 V: 31; NOVEMBER'22 V: 30; DECEMBER'22 V: 28 | PM 1500 |  | container if needed)
|  | REAL DATE | [60 empty] | 1. All item PM 750
|  | HM REAL | [60 empty] | 2. Insulation Motor Measure
|  |  | JANUARY'22 I: Remarks : | (Boogie, Gantry, Hoist, ACM,Trolley)
|  |  | JANUARY'22 I: .; JANUARY'22 II: PM 250H; FEBRUARY'22 I: PM 500H; FEBRUARY'22 V: PM 750H; MARCH'22 IV: PM 1500 H; APRIL'22 III: PM 3000H; MEI'22 II: PM 6000H | 3.
Preventive Maintenance
[64 empty] | . | PM 250H
PM 500H
PM 750H
PM 1500 H
PM 3000H
PM 6000H
|  |  |  | Diperiksa Oleh, | [43 empty] | Dibuat Oleh,
|  |  |  | Ifsan Rosady | [43 empty] | Augusto Dwifa Daniel
|  |  |  | Asisten Manajer Peralatan | [43 empty] | Supervisi Alat Bongkar Muat Lapangan

## Sheet2 (hidden)
2019-11-04 | 2019-11-14 | 2019-11-14 | 2019-12-02 | 2019-12-17 | 2020-01-01 | 2020-01-15 | 2020-01-29 | 2020-02-12 | 2020-02-26 | 2020-03-11 | 2020-03-25 | 2020-04-08 | 2020-04-22 | 2020-05-06 | 2020-05-20 | 2020-06-03 | 2020-06-17 | 2020-07-01 | 2020-07-15 | 2020-07-29 | 2020-08-12 | 2020-08-26 | 2020-09-09 | 2020-09-23 | 2020-10-07 | 2020-10-21 | 2020-11-04 | 2020-11-18
250 | 500 | 750 | 1000 | 1250 | 1500 | 1750 | 2000 | 2250 | 2500 | 2750 | 3000 | 3250 | 3500 | 3750 | 4000 | 4250 | 4500 | 4750 | 5000 | 5250 | 5500 | 5750 | 6000 | 6250 | 6500 | 6750 | 7000 | 7250
250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 251 | 501
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
2019-11-06 | 2019-11-15 | 2019-12-03 | 2019-12-17 | 2019-12-31 | 2020-01-14 | 2020-01-28 | 2020-02-11 | 2020-02-25 | 2020-03-10 | 2020-03-24 | 2020-04-07 | 2020-04-21 | 2020-05-05 | 2020-05-19 | 2020-06-02 | 2020-06-16 | 2020-06-30 | 2020-07-14 | 2020-07-28 | 2020-08-11 | 2020-08-25 | 2020-09-08 | 2020-09-22 | 2020-10-06 | 2020-10-20 | 2020-11-03 | 2020-11-17 | 2020-12-01
250 | 500 | 750 | 1000 | 1250 | 1500 | 1750 | 2000 | 2250 | 2500 | 2750 | 3000 | 3250 | 3500 | 3750 | 4000 | 4250 | 4500 | 4750 | 5000 | 5250 | 5500 | 5750 | 6000 | 6250 | 6500 | 6750 | 7000 | 7250
250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 251 | 501 | 15
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 255
|  | 2019-12-20 | 2020-01-09 | 2020-01-29 | 2020-02-18 | 2020-03-09 | 2020-03-29 | 2020-04-18 | 2020-05-08 | 2020-05-28 | 2020-06-17 | 2020-07-07 | 2020-07-27 | 2020-08-16 | 2020-09-05 | 2020-09-25 | 2020-10-15 | 2020-11-04 | 2020-11-24 | 2020-12-14 | 2021-01-03 | 2021-01-23 | 2021-02-12 | 2021-03-04 | 2021-03-24 | 2021-04-13 | 2021-05-03 | 2021-05-23
|  | 250 | 500 | 750 | 1000 | 1250 | 1500 | 1750 | 2000 | 2250 | 2500 | 2750 | 3000 | 3250 | 3500 | 3750 | 4000 | 4250 | 4500 | 4750 | 5000 | 5250 | 5500 | 5750 | 6000 | 6250 | 6500 | 6750
|  | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 251 | 501
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  | 2019-12-17 | 2020-01-09 | 2020-02-01 | 2020-02-24 | 2020-03-18 | 2020-04-10 | 2020-05-03 | 2020-05-26 | 2020-06-18 | 2020-07-11 | 2020-08-03 | 2020-08-26 | 2020-09-18 | 2020-10-11 | 2020-11-03 | 2020-11-26 | 2020-12-19 | 2021-01-11 | 2021-02-04 | 2021-02-28 | 2021-03-24 | 2021-04-17 | 2021-05-11 | 2021-06-04 | 2021-06-28 | 2021-07-22 | 2021-08-05
|  | 2019-12-12 | 2019-12-30 | 2020-01-17 | 2020-02-04 | 2020-02-22 | 2020-03-11 | 2020-03-29 | 2020-04-16 | 2020-05-04 | 2020-05-22 | 2020-06-09 | 2020-06-27 | 2020-07-15 | 2020-08-02 | 2020-08-20 | 2020-09-07 | 2020-09-25 | 2020-10-13 | 2020-10-31 | 2020-11-18
|  | 250 | 500 | 750 | 1000 | 1250 | 1500 | 1750 | 2000 | 2250 | 2500 | 2750 | 3000 | 3250 | 3500 | 3750 | 4000 | 4250 | 4500 | 4750 | 5000 | 5250 | 5500 | 5750 | 6000 | 6250 | 6500 | 6750
|  | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 251 | 501
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  | 2019-12-28 | 2020-01-25 | 2020-02-22 | 2020-03-21 | 2020-04-18 | 2020-05-16 | 2020-06-13 | 2020-07-11 | 2020-08-08 | 2020-09-05 | 2020-10-03 | 2020-10-31 | 2020-11-28
|  | 500 | 1000 | 1500 | 2000 | 2500 | 3000 | 3500 | 4000 | 4500 | 5000 | 5500 | 6000 | 6500
|  | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | 2019-12-20 | 2020-01-12 | 2020-02-04 | 2020-02-27 | 2020-03-21 | 2020-04-13 | 2020-05-06 | 2020-05-29 | 2020-06-21 | 2020-07-14 | 2020-08-06 | 2020-08-29 | 2020-09-21 | 2020-10-14 | 2020-11-06
|  | 500 | 1000 | 1500 | 2000 | 2500 | 3000 | 3500 | 4000 | 4500 | 5000 | 5500 | 6000 | 6500
|  | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | 2019-12-02 | 2019-12-16 | 2019-12-30 | 2020-01-13 | 2020-01-27 | 2020-02-10 | 2020-02-24 | 2020-03-09 | 2020-03-23 | 2020-04-06 | 2020-04-20 | 2020-05-04 | 2020-05-18 | 2020-06-01 | 2020-06-15 | 2020-06-29 | 2020-07-13 | 2020-07-27 | 2020-08-10 | 2020-08-24 | 2020-09-07 | 2020-09-21 | 2020-10-05 | 2020-10-19 | 2020-11-02 | 2020-11-16
|  | 2019-12-06 | 2019-12-24 | 2020-01-11 | 2020-01-29 | 2020-02-16 | 2020-03-05 | 2020-03-23 | 2020-04-10 | 2020-04-28 | 2020-05-16 | 2020-06-03 | 2020-06-21 | 2020-07-09 | 2020-07-27 | 2020-08-14 | 2020-09-01 | 2020-09-19 | 2020-10-07 | 2020-10-25 | 2020-11-12 | 2020-11-30
|  | 500 | 1000 | 501 | 1001 | 502 | 1002 | 503 | 1003 | 504 | 1004 | 505 | 1005 | 506 | 1006 | 507 | 1007 | 508 | 1008 | 509
|  | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 500 | 250
|  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | 2019-12-20 | 2020-01-11 | 2020-02-02 | 2020-02-24 | 2020-03-17 | 2020-04-08 | 2020-04-30 | 2020-05-22 | 2020-06-13 | 2020-07-05 | 2020-07-27 | 2020-08-18 | 2020-09-09 | 2020-10-01 | 2020-10-23 | 2020-11-14 | 2020-12-06
|  | 2019-12-02 | 2019-12-16 | 2019-12-30 | 2020-01-13 | 2020-01-27 | 2020-02-10 | 2020-02-24 | 2020-03-09 | 2020-03-23 | 2020-04-06 | 2020-04-20 | 2020-05-04 | 2020-05-18 | 2020-06-01 | 2020-06-15 | 2020-06-29 | 2020-07-13 | 2020-07-27 | 2020-08-10 | 2020-08-24 | 2020-09-07 | 2020-09-21 | 2020-10-05 | 2020-10-19 | 2020-11-02 | 2020-11-16
|  | 2019-12-16 | 2020-01-10 | 2020-02-04 | 2020-02-29 | 2020-03-25 | 2020-04-19 | 2020-05-14 | 2020-06-08 | 2020-07-03 | 2020-07-28 | 2020-08-22 | 2020-09-16 | 2020-10-11 | 2020-11-05 | 2020-11-30
|  | 2019-12-02 | 2019-12-25 | 2020-01-17 | 2020-02-09 | 2020-03-03 | 2020-03-26 | 2020-04-18 | 2020-05-11 | 2020-06-03 | 2020-06-26 | 2020-07-19 | 2020-08-11 | 2020-09-03 | 2020-09-26 | 2020-10-19 | 2020-11-11
|  | 2019-12-30 | 2020-01-16 | 2020-02-02 | 2020-02-19 | 2020-03-07 | 2020-03-24 | 2020-04-10 | 2020-04-27 | 2020-05-14 | 2020-05-31 | 2020-06-17 | 2020-07-04 | 2020-07-21 | 2020-08-07 | 2020-08-24 | 2020-09-10 | 2020-09-27 | 2020-10-14 | 2020-10-31 | 2020-11-17 | 2020-12-04
|  | 2019-12-03 | 2019-12-17 | 2019-12-31 | 2020-01-14 | 2020-01-28 | 2020-02-11 | 2020-02-25 | 2020-03-10 | 2020-03-24 | 2020-04-07 | 2020-04-21 | 2020-05-05 | 2020-05-19 | 2020-06-02 | 2020-06-16 | 2020-06-30 | 2020-07-14 | 2020-07-28 | 2020-08-11 | 2020-08-25 | 2020-09-08 | 2020-09-22 | 2020-10-06 | 2020-10-20 | 2020-11-03 | 2020-11-17
|  | 2019-12-03 | 2019-12-28 | 2020-01-22 | 2020-02-16 | 2020-03-12 | 2020-04-06 | 2020-05-01 | 2020-05-26 | 2020-06-20 | 2020-07-15 | 2020-08-09 | 2020-09-03 | 2020-09-28 | 2020-10-23 | 2020-11-17
|  | 2019-12-17 | 2020-01-09 | 2020-02-01 | 2020-02-24 | 2020-03-18 | 2020-04-10 | 2020-05-03 | 2020-05-26 | 2020-06-18 | 2020-07-11 | 2020-08-03 | 2020-08-26 | 2020-09-18 | 2020-10-11 | 2020-11-03 | 2020-11-26
|  | 2019-12-03 | 2019-12-20 | 2020-01-06 | 2020-01-23 | 2020-02-09 | 2020-02-26 | 2020-03-14 | 2020-03-31 | 2020-04-17 | 2020-05-04 | 2020-05-21 | 2020-06-07 | 2020-06-24 | 2020-07-11 | 2020-07-28 | 2020-08-14 | 2020-08-31 | 2020-09-17 | 2020-10-04 | 2020-10-21 | 2020-11-07 | 2020-11-24 | 2020-12-11

## Sheet3 (hidden)
No | Part Name | Volume |  | Period | Stock Teknik | 9
Engine Type: QSK50-G7, SN: 33215621, CUMMINS
1 | Fuel Separator Filter Fleetguard FS 53014 | 1 | Pcs | 250. H
2 | Engine Oil Premium Blue 15 W/40 Valvoline | 200 | Ltr | 500. H
3 | Lube Filter Fleetguard LF 9050 | 4 | Pcs | 500. H
4 | Fuel Filter FF 5782 NN | 3 | Pcs | 500. H
5 | Coolant Filter Fleetguard WF 2076 | 2 | Pcs | 500. H
6 | Air Filter Fleetguard AF 25593 | 2 | Pcs | 3000. H
7 | Grease Wirerope |  |  | 250. H
8 | Grease Bearing
9 | Grease Bearing Motor/Generator
10 | Oil Gearbox |  |  | 1500. H